## Solved Problem 1
Chapter 3 - Solved Problem 1
Assignment: (completed)
1. Develop formulas for the ES/EF columns (Hint: use MAX function)
2. Develop formulas for the LS/LF columns (Hint: use MIN function)
3. Answer parts b, c, & d.
Immediate Predecessors
Activity | Time | P1 | P2 | Earliest Start | Earliest Finish | Latest Finish | Latest Start | Slack
A | 1 |  |  | 0 | 1 | 1 | 0 | 0
B | 4 | A |  | 1 | 5 | 5 | 1 | 0
C | 3 | A |  | 1 | 4 | 9 | 6 | 5
D | 7 | A |  | 1 | 8 | 9 | 2 | 1
E | 6 | B |  | 5 | 11 | 11 | 5 | 0
F | 2 | C | D | 8 | 10 | 11 | 9 | 1
G | 7 | E | F | 11 | 18 | 18 | 11 | 0
H | 9 | D |  | 8 | 17 | 18 | 9 | 1
I | 4 | G | H | 18 | 22 | 22 | 18 | 0
Answers:
b. See above
c. Critical path is A - B - E - G - I | [6 empty] | (Activities on Critical Path shown in | Yellow)
d. Change F's time to 4, the critical path changes with a completion time of 23.

## Solved Problem 2
Chapter 3: Solved Problem 2 (Activity crashing)
= Activities on the Critical Path
= Activities available for crashing on Critical Path
Immediate Predecessors
Activity | Normal | P1 | P2 | ES | EF | LF | LS | Slack
A | 4 |  |  | 0 | 4 | 4 | 0 | 0
B | 3 | A |  | 4 | 7 | 7 | 4 | 0
C | 2 | A |  | 4 | 6 | 9 | 7 | 3
D | 5 | B |  | 7 | 12 | 12 | 7 | 0
E | 1 | B | C | 7 | 8 | 12 | 11 | 4
F | 3 | C |  | 6 | 9 | 12 | 9 | 3
G | 4 | E | F | 9 | 13 | 16 | 12 | 3
H | 4 | D | E | 12 | 16 | 16 | 12 | 0
I | 6 | H | G | 16 | 22 | 22 | 16 | 0
Activity | Activity Times |  | Activity Costs |  | Cost/ Week | Crash Weeks | Activity Cost
| Normal | Crash | Normal | Crash
A | 4 | 2 | 10000 | 11000 | 500 | 0 | 10000
B | 3 | 2 | 6000 | 9000 | 3000 | 0 | 6000
C | 2 | 1 | 4000 | 6000 | 2000 | 0 | 4000
D | 5 | 3 | 14000 | 18000 | 2000 | 0 | 14000
E | 1 | 1 | 9000 | 9000 |  | 0 | 9000
F | 3 | 2 | 7000 | 8000 | 1000 | 0 | 7000
G | 4 | 2 | 13000 | 25000 | 6000 | 0 | 13000
H | 4 | 1 | 11000 | 18000 | 2333.3333 | 0 | 11000
I | 6 | 5 | 20000 | 29000 | 9000 | 0 | 20000
|  | Normal Cost to Complete = | 94000 |  |  | Crash Cost to Complete= | 94000
|  | 22 | = Time to complete project
|  | 94000 | = Cost to complete project
Note on H19: Alter The number of crash weeks.