## 6-4
PROBLEM NO. 6 - 4
Task | Length (minutes) | Immediate Follower
a | 0.2 | b
b | 0.4 | d
c | 0.3 | d
d | 1.3 | g
e | 0.1 | f
f | 0.8 | g
g | 0.3 | h
h | 1.2 | end

## 6-5
PROBLEM NO. 6 - 5
Task | Duration (minutes) | Precedes Task
a | 0.2 | b
b | 0.4 | c
c | 0.2 | f
d | 0.4 | e
e | 1.2 | g
f | 1.2 | g
g | 1 | end

## 6-6
PROBLEM NO. 6 - 6
Task | Length (minutes) | Follows Task
a | 0.1 | —
b | 0.2 | a
c | 0.9 | b
d | 0.6 | c
e | 0.1 | —
f | 0.2 | d,e
g | 0.4 | f
h | 0.1 | g
i | 0.2 | h
j | 0.7 | i,
k | 0.3 | j
l | 0.2 | k

## 6-7
PROBLEM NO. 6 - 7
Task | Task Time (seconds) | Immediate Predecessors
A | 45 | —
B | 11 | A
C | 9 | B
D | 50 | —
E | 26 | D
F | 11 | E
G | 12 | C
H | 10 | C
I | 9 | F,G,H
J | 10 | I
193

## 6-8
PROBLEM NO. 6 - 8
Task | Immediately Precedes Task(s) | Task Time
a | b,c,d | 0.5
b | e | 1.4
c | e | 1.2
d | f | 0.7
e | g , j | 0.5
f | I | 1.0
g | h | 0.4
h | k | 0.3
i | j | 0.5
j | k | 0.8
k | m | 0.9
m | end | 0.3

## 6-14
PROBLEM NO. 6 - 14
|  | DISTANCE BETWEEN LOCATIONS (meters) | [5 empty] | NUMBER OF TRIPS PER DAY BETWEEN DEPARTMENTS
From | To | A | B | C | D | From | To | 1 | 2 | 3 | 4
A |  | — | 40 | 80 | 70 | 1 |  | — | 10 | 20 | 80
B |  |  | — | 40 | 50 | 2 |  |  | — | 40 | 90
C |  |  |  | — | 60 | 3 |  |  |  | — | 55
D |  |  |  |  | — | 4 |  |  |  |  | —

## 6-15
PROBLEM NO. 6 - 15
DISTANCE (meters)
From | To | A | B | C | D | E | F | G | H
A |  | — | 40 | 40 | 60 | 120 | 80 | 100 | 110
B |  |  | — | 60 | 40 | 60 | 140 | 120 | 130
C |  |  |  | — | 45 | 85 | 40 | 70 | 90
D | DISTANCE (meters) D: —; DISTANCE (meters) E: 40; DISTANCE (meters) F: 50; DISTANCE (meters) G: 40; DISTANCE (meters) H: 45
E | DISTANCE (meters) E: —; DISTANCE (meters) F: 90; DISTANCE (meters) G: 50; DISTANCE (meters) H: 40
F | DISTANCE (meters) F: —; DISTANCE (meters) G: 40; DISTANCE (meters) H: 60
G | DISTANCE (meters) G: —; DISTANCE (meters) H: 40
H | bar: DISTANCE (meters) H
LOADS PER DAY
From | To | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
1 |  | — | 10 | 5 | 90 | 370 | 135 | 125 | 0
2 |  |  | — | 360 | 120 | 40 | 115 | 45 | 120
3 |  |  |  | — | 350 | 110 | 40 | 20 | 200
4 |  |  |  |  | — | 190 | 70 | 50 | 190
5 |  | LOADS PER DAY 5: —; LOADS PER DAY 6: 10; LOADS PER DAY 7: 40; LOADS PER DAY 8: 10
6 |  | LOADS PER DAY 6: —; LOADS PER DAY 7: 50; LOADS PER DAY 8: 20
7 |  | LOADS PER DAY 7: —; LOADS PER DAY 8: 20
8 | bar: LOADS PER DAY 8

## 6-16
PROBLEM NO. 6 - 16
DISTANCE BETWEEN LOCATIONS (meters)
From | To | A | B | C | D | E | F
A |  | — | 40 | 80 | 100 | 120 | 160
B |  |  | — | 40 | 60 | 80 | 120
C |  |  |  | — | 20 | 40 | 80
D |  |  |  |  | — | 20 | 40
E | [5 empty] | — | 40
F | [6 empty] | —
|  | TRIPS BETWEEN DEPARTMENTS (per day) | TRIPS BETWEEN DEPARTMENTS ( PER DAY)
| To | Reception | 1 | 2 | 3 | 4 | 5 | 6
Reception |  | — | 20 | 50 | 210 |  | 10 | 130
1 |  | 10 | — | 0 | 40 | 110 | 80 | 50
2 |  | 40 |  | — | 0 | 50 | 40 | 120
3 |  | 10 |  |  | — | 10 | 250 | 10
4 |  | 0 | TRIPS BETWEEN DEPARTMENTS ( PER DAY) 4: —; TRIPS BETWEEN DEPARTMENTS ( PER DAY) 5: 40; TRIPS BETWEEN DEPARTMENTS ( PER DAY) 6: 90
5 |  | 10 | TRIPS BETWEEN DEPARTMENTS ( PER DAY) 5: —; TRIPS BETWEEN DEPARTMENTS ( PER DAY) 6: 20
6 |  | 30 | bar: TRIPS BETWEEN DEPARTMENTS ( PER DAY) 6

## 6-17
PROBLEM NO. 6 - 17
NUMBER OF TRIPS PER DAY BETWEEN DEPARTMENTS
From | To | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
1 |  | — | 40 | 51 | 26 | 23 | 9 | 20 | 12 | 11 | 35
2 |  |  | — | 37 | 16 | 27 | 15 | 18 | 18 | 18 | 36
3 |  |  |  | — | 18 | 20 | 14 | 50 | 18 | 25 | 36
4 |  |  |  |  | — | 35 | 14 | 14 | 22 | 23 | 31
5 | [5 empty] | — | 24 | 14 | 13 | 21 | 25
6 |  | NUMBER OF TRIPS PER DAY BETWEEN DEPARTMENTS 6: —; NUMBER OF TRIPS PER DAY BETWEEN DEPARTMENTS 7: 17; NUMBER OF TRIPS PER DAY BETWEEN DEPARTMENTS 8: 44; NUMBER OF TRIPS PER DAY BETWEEN DEPARTMENTS 9: 42; NUMBER OF TRIPS PER DAY BETWEEN DEPARTMENTS 10: 25
7 |  | NUMBER OF TRIPS PER DAY BETWEEN DEPARTMENTS 7: —; NUMBER OF TRIPS PER DAY BETWEEN DEPARTMENTS 8: 14; NUMBER OF TRIPS PER DAY BETWEEN DEPARTMENTS 9: 33; NUMBER OF TRIPS PER DAY BETWEEN DEPARTMENTS 10: 40
8 |  | NUMBER OF TRIPS PER DAY BETWEEN DEPARTMENTS 8: —; NUMBER OF TRIPS PER DAY BETWEEN DEPARTMENTS 9: 43; NUMBER OF TRIPS PER DAY BETWEEN DEPARTMENTS 10: 35
9 |  | NUMBER OF TRIPS PER DAY BETWEEN DEPARTMENTS 9: —; NUMBER OF TRIPS PER DAY BETWEEN DEPARTMENTS 10: 47
10 | bar: NUMBER OF TRIPS PER DAY BETWEEN DEPARTMENTS 10