## 17-2
PROBLEM NO. 17 - 2
Estimated Time (hrs.) | Activity (abbreviation)
0.8 | Install software (Inst)
0.4 | Outline the paper (Out)
0.2 | Submit paper to Instructor (Sub)
0.6 | Choose a topic (Ch)
0.5 | Use grammar-checking routine and make corrections (Ck)
3 | Write the paper using the word-processing software (Write)
2 | Shop for new computer (Sh)
1 | Select and purchase computer (Sel)
2 | Library research on chosen topic (Lib)

## 17-4
PROBLEM NO. 17 - 4
(1) Activity | Immediate Predecessor | (2) Activity | Immediate Predecessor
A | — | J | —
B | — | K | —
C | — | L | J
D | A | M | L
E | B | N | J
F | B | P | N
G | C | Q | —
H | F | R | K
I | F,G | S | Q
K | D | V | R,S,T
End | H,I,K | T | Q
|  | W | T
|  | End | M,P,V,W

## 17-7
PROBLEM NO. 17 - 7
TIME IN DAYS
Activity | Immediate Predecessor | Optimistic | Most Likely | Pessimistic
A | — | 5 | 6 | 7
B | — | 8 | 8 | 11
C | A | 6 | 8 | 11
D | — | 9 | 12 | 15
E | C | 5 | 6 | 9
F | D | 5 | 6 | 7
G | F | 2 | 3 | 7
H | B | 4 | 4 | 5
I | H | 5 | 7 | 8
End | E,G,I

## 17-8
PROBLEM NO. 17 - 8
Path | Expected Duration (weeks) | Variance
A… | 10 | 1.21
B… | 8 | 2
C… | 12 | 1
D… | 15 | 2.89
E… | 14 | 1.44

## 17-9
PROBLEM NO. 17 - 9
Activity | Mean | Standard Deviation
1-2 | 5 | 1.3
2-3 | 4 | 1
1-3 | 8 | 1.6

## 17-10
PROBLEM NO. 17 - 10
Activity | Estimated Time (weeks) | Standard Deviation (weeks)
1-2 | 4 | 0.7
2-4 | 6 | 0.9
1-3 | 3 | 0.62
3-4 | 9 | 1.9

## 17-12
PROBLEM NO. 17 - 12
Activity | Immediate Predecessor | Estimated Times (weeks)
A… | — | 2-4-6
D… | A | 6-8-10
E… | D | 7-9-12
H… | E | 2-3-5
F… | A | 3-4-8
G… | F | 5-7-9
B… | — | 2-2-3
I… | B | 2-3-6
J… | I | 3-4-5
K… | I | 4-5-8
C… | — | 5-8-12
M… | C | 1-1-1
N… | M | 6-7-11
O… | N | 8-9-13
End… | H,G,K,O

## 17-14
PROBLEM NO. 17 - 14
CRASHING COSTS
Activity | Immediate Predecessor | Normal Time (Weeks) | First Week | Second Week
A… | — | 12 | $15000 | $20000
B… | A | 14 | 10000 | 10000
C… | — | 10 | 5000 | 5000
D… | C | 17 | 20000 | 21000
E… | C | 18 | 16000 | 18000
F… | C | 12 | 12000 | 15000
G… | D | 15 | 24000 | 24000
H… | E | 8 | — | —
I… | F | 7 | 30000 | —
J… | I | 12 | 25000 | 25000
K… | B | 9 | 10000 | 10000
M… | G | 3 | — | —
N… | H | 11 | 40000 | —
P… | H,J | 8 | 20000 | 20000
End… | K,I,M,N,P

## 17-15
PROBLEM NO. 17 - 15
CRASHING COSTS ($000)
Activity | First Week | Second Week | Third Week
1-2… | $18 | $22 | $—
2-5… | 24 | 25 | 25
5-7… | 30 | 30 | 35
7-11… | 15 | 20 | —
11-13… | 30 | 33 | 36
1-3… | 12 | 24 | 26
3-8… | — | — | —
8-11… | 40 | 40 | 40
3-9… | 3 | 10 | 12
9-12… | 2 | 7 | 10
12-13… | 26 | — | —
1-4… | 10 | 15 | 25
4-6… | 8 | 13 | —
6-10… | 5 | 12 | —
10-12… | 14 | 15 | —

## 17-16
PROBLEM NO. 17 - 16
CRASHING COSTS
Activity | Immediate Predecessor | Normal Time (weeks) | 1st Week | 2nd Week
K | — | 9 | $410 | $415
L | K | 7 | 125 | —
N | K | 5 | 45 | 45
M | L | 4 | 300 | 350
J | N | 6 | 50 | —
Q | J,M | 5 | 200 | 225
P | Q | 8 | — | —
Y | Q | 7 | 85 | 90
Z | P | 6 | 90 | —
End | Y,Z

## 17-18
PROBLEM NO. 17 - 18
Event | Probability | Cost ($000)
1 | 0.25 | 15
2 | 0.35 | 25
3 | 0.2 | 55
4 | 0.8 | 10
5 | 0.1 | 77
6 | 0.4 | 55
7 | 0.6 | 50

## 17-19
PROBLEM NO. 17 - 19
Event | Cost ($000) | Probability
Equipment breakdown | 40 | 0.2
Vendor is late with key segment | 210 | 0.6
Subcontractor has labor issues | 140 | 0.3
Weather problems | 15 | Unknown
Funding delays | 50 | 0.40 to 0.60
Testing delays | 20 | 0.4

## Case
Time, Please
Path | Expected Duration (weeks) | Standard Deviation
A | 10 | 4
B | 14 | 2
C | 13 | 2