## Chapter 17
Excel Templates to accompany Operations Management, Second Edition, Asia Global Edition
created by Lee Tangedahl
Copyright © 2014 by McGraw-Hill Education Asia. All rights reserved.
Chapter Seventeen - Project Management
| Templates: | Pert/CPM with Deterministic Time Estimates
Pert/CPM, Probabilistic Time Estimates
Pert/CPM, Probabilistic Completion Time
Time-Cost Tradeoffs: Crashing
|  | Lecture Suggestions | Solved Problems: | Solved Problem 1
Solved Problem 2
| Examples: | Example 2-4 |  | Solved Problem 3
|  | Example 5 |  | Solved Problem 4
Example 6
Example 7
See Instructions template for complete instructions.

## PERT, Deterministic
Pert/CPM with Deterministic Time Estimates
Note: use AOA notation with ascending nodes numbers from beginning to end.
<Back
| Activity | Start | End | Time | ES | EF | LF | LS | Slack
| a1 | 1 | 2 | 8 | 0 | 8 | 8 | 0 | 0
| a2 | 2 | 4 | 6 | 8 | 14 | 16 | 10 | 2
| a3 | 1 | 3 | 4 | 0 | 4 | 10 | 6 | 6
| a4 | 3 | 5 | 9 | 4 | 13 | 19 | 10 | 6
| a5 | 2 | 5 | 11 | 8 | 19 | 19 | 8 | 0
| a6 | 4 | 5 | 3 | 14 | 17 | 19 | 16 | 2
| a7 | 5 | 6 | 1 | 19 | 20 | 20 | 19 | 0

## PERT, Probabilistic
Pert/CPM, Probabilistic Time Estimates
Note: use AOA notation with ascending nodes numbers from beginning to end.
<Back
| Activity | Start | End | a | m | b | Var | E(T) | ES | EF | LF | LS | Slack
| a | 1 | 2 | 1 | 3 | 4 | 0.25 | 2.8333 | 0 | 2.8333 | 8.8333 | 6 | 6
| b | 2 | 5 | 2 | 4 | 6 | 0.44444 | 4 | 2.8333 | 6.8333 | 12.8333 | 8.8333 | 6
| c | 5 | 8 | 2 | 3 | 5 | 0.25 | 3.1667 | 6.8333 | 10 | 16 | 12.8333 | 6
| d | 1 | 3 | 3 | 4 | 5 | 0.11111 | 4 | 0 | 4 | 4 | 0 | 0
| e | 3 | 6 | 3 | 5 | 7 | 0.44444 | 5 | 4 | 9 | 9 | 4 | 0
| f | 6 | 8 | 5 | 7 | 9 | 0.44444 | 7 | 9 | 16 | 16 | 9 | 0
| g | 1 | 4 | 2 | 3 | 6 | 0.44444 | 3.3333 | 0 | 3.3333 | 5.8333 | 2.5 | 2.5
| h | 4 | 7 | 4 | 6 | 8 | 0.44444 | 6 | 3.3333 | 9.3333 | 11.8333 | 5.8333 | 2.5
| i | 7 | 8 | 3 | 4 | 6 | 0.25 | 4.1667 | 9.3333 | 13.5 | 16 | 11.8333 | 2.5

## PERT, Completion
Pert/CPM, Probabilistic Completion Time
<Back
|  | Path | Expected Times |  |  |  |  | E(t) | Variances |  |  |  |  | spath | Probability
| 1 | 1-2-5-8 | 2.8333 | 4 | 3.1667 |  |  | 10 | 0.25 | 0.44444 | 0.25 |  |  | 0.97183 | 1
| 2 | 1-3-6-8 | 4 | 5 | 7 |  |  | 16 | 0.11111 | 0.44444 | 0.44444 |  |  | 1 | 0.84134
| 3 | 1-4-7-8 | 3.3333 | 6 | 4.1667 |  |  | 13.5 | 0.44444 | 0.44444 | 0.25 |  |  | 1.0672 | 0.99948
4
5
6
7
8
[7 empty] | Projected Completion Time: | 17 | [5 empty] | Probability of Completion: | 0.84091
[11 empty] | 12.5 | 0.00087268
[11 empty] | 13.2 | 0.0079155
|  | Probability of completion for single path | [8 empty] | 13.9 | 0.043984
|  | (select path number from table above): | [8 empty] | 14.6 | 0.14973
[11 empty] | 15.3 | 0.31225
|  |  | Path |  | E(t) | spath | Probability |  |  |  | 16 | 0.39894
|  | 2 | 1-3-6-8 |  | 16 | 1 | 0.84134 |  |  |  | 16.7 | 0.31225
[11 empty] | 17.4 | 0.14973
[11 empty] | 18.1 | 0.043984
[11 empty] | 18.8 | 0.0079155
[11 empty] | 19.5 | 0.00087268
[11 empty] | 17 |  | 0
[11 empty] | 17 |  | 0.39894
[11 empty] | 6.2648 | 46 | 0
[11 empty] | 19.7352 | 19.7352 | 0

## PERT, Crashing
Time-Cost Tradeoffs: Crashing
| Note: | use AOA notation with ascending nodes numbers from beginning to end.
<Back |  | Step 1: | Enter Activity, Start, End, Normal Time data. Initially Crashing Time and Cost
columns must be blank. (Note: delete F14:G43 below to re-start problem.)
|  | Step 2: | Press Solve
|  | Step 3: | Select feasible activity(ies) on critical path(s) to crash, if there are no feasible
activities, you are done.
|  | Step 4: | Enter Crashing Time and Cost in the row(s) for activity(ies) selected in step 3.
Go to Step 2.
[11 empty] | Project Completion Time: | 17
[11 empty] | Crashing Cost: | 1700
|  |  |  | Normal | Crashing
| Activity | Start | End | Time | Time | Cost | Time | ES | EF | LF | LS | Slack
| a | 1 | 2 | 6 |  |  | 6 | 0 | 6 | 6 | 0 | 0
| b | 2 | 5 | 10 |  |  | 10 | 6 | 16 | 16 | 6 | 0
| c | 1 | 3 | 5 | 1 | 300 | 4 | 0 | 4 | 4 | 0 | 0
| d | 3 | 4 | 4 |  |  | 4 | 4 | 8 | 8 | 4 | 0
| e | 4 | 5 | 9 | 1 | 600 | 8 | 8 | 16 | 16 | 8 | 0
| f | 5 | 6 | 2 | 1 | 800 | 1 | 16 | 17 | 17 | 16 | 0

## Lecture
Lecture Suggestions - Chapter 17
<Back
Example 7: Time-Cost Tradeoffs: Crashing
1. | Select the Example 7 worksheet
2. | (Optional) Clear worksheet (press Clear and confirm with OK) and re-enter data for Activity, Start,
End, and Normal time.
3. | If you did not Clear all data, clear Crashing Time and Cost columns (select and press delete).
4. | Press the Solve button, the resulting solution shows that the project can be completed in 20 days
and activities c, d, e, and f are on the critical path (indicated by red).
5. | Select job to be crashed: select C (lowest cost on critical path) and enter Crashing Time = 1 and
Crashing Cost =300.
6 | Press Solve button, the resulting solution shows that the project cam be completed in 19 days with
a total crash cost = 300.
Repeat steps 5 and 6:
7. | Select job to be crashed: select E (lowest cost on critical path) and enter Crashing Time = 1 and
Crashing Cost =600.
8. | Press Solve button, the resulting solution shows that the project cam be completed in 18 days with
a total crash cost = 900.
Repeat steps 5 and 6:
7. | Select job to be crashed: select F (lowest cost on critical path) and enter Crashing Time = 1 and
Crashing Cost =800.
8. | Press Solve button, the resulting solution shows that the project cam be completed in 17 days with
a total crash cost = 1700.
9. | At this point all activities are on the critical path (indicated in red) and no further crashing is possible.

## Example 2-4
Pert/CPM with Deterministic Time Estimates
Note: use AOA notation with ascending nodes numbers from beginning to end.
<Back
Note: delete cells F6:J35 to demonstrate solution.
| Activity | Start | End | Time | ES | EF | LF | LS | Slack
| a1 | 1 | 2 | 8 | 0 | 8 | 8 | 0 | 0
| a2 | 2 | 4 | 6 | 8 | 14 | 16 | 10 | 2
| a3 | 1 | 3 | 4 | 0 | 4 | 10 | 6 | 6
| a4 | 3 | 5 | 9 | 4 | 13 | 19 | 10 | 6
| a5 | 2 | 5 | 11 | 8 | 19 | 19 | 8 | 0
| a6 | 4 | 5 | 3 | 14 | 17 | 19 | 16 | 2
| a7 | 5 | 6 | 1 | 19 | 20 | 20 | 19 | 0

## Example 5
Pert/CPM, Probabilistic Time Estimates
Note: use AOA notation with ascending nodes numbers from beginning to end.
<Back
Note: delete some or all of the cells J6:N35 to demonstrate solution.
| Activity | Start | End | a | m | b | Var | E(T) | ES | EF | LF | LS | Slack
| a | 1 | 2 | 1 | 3 | 4 | 0.25 | 2.8333 | 0 | 2.8333 | 8.8333 | 6 | 6
| b | 2 | 5 | 2 | 4 | 6 | 0.44444 | 4 | 2.8333 | 6.8333 | 12.8333 | 8.8333 | 6
| c | 5 | 8 | 2 | 3 | 5 | 0.25 | 3.1667 | 6.8333 | 10 | 16 | 12.8333 | 6
| d | 1 | 3 | 3 | 4 | 5 | 0.11111 | 4 | 0 | 4 | 4 | 0 | 0
| e | 3 | 6 | 3 | 5 | 7 | 0.44444 | 5 | 4 | 9 | 9 | 4 | 0
| f | 6 | 8 | 5 | 7 | 9 | 0.44444 | 7 | 9 | 16 | 16 | 9 | 0
| g | 1 | 4 | 2 | 3 | 6 | 0.44444 | 3.3333 | 0 | 3.3333 | 5.8333 | 2.5 | 2.5
| h | 4 | 7 | 4 | 6 | 8 | 0.44444 | 6 | 3.3333 | 9.3333 | 11.8333 | 5.8333 | 2.5
| i | 7 | 8 | 3 | 4 | 6 | 0.25 | 4.1667 | 9.3333 | 13.5 | 16 | 11.8333 | 2.5

## Example 6
Pert/CPM, Probabilistic Completion Time
<Back
|  | Path | Expected Times |  |  |  |  | E(t) | Variances |  |  |  |  | spath | Probability
| 1 | 1-2-5-8 | 2.8333 | 4 | 3.1667 |  |  | 10 | 0.25 | 0.44444 | 0.25 |  |  | 0.97183 | 1
| 2 | 1-3-6-8 | 4 | 5 | 7 |  |  | 16 | 0.11111 | 0.44444 | 0.44444 |  |  | 1 | 0.84134
| 3 | 1-4-7-8 | 3.3333 | 6 | 4.1667 |  |  | 13.5 | 0.44444 | 0.44444 | 0.25 |  |  | 1.0672 | 0.99948
4
5
6
7
8
[7 empty] | Projected Completion Time: | 17 | [5 empty] | Probability of Completion: | 0.84091
[11 empty] | 12.5 | 0.00087268
[11 empty] | 13.2 | 0.0079155
|  | Probability of completion for single path | [8 empty] | 13.9 | 0.043984
|  | (select path number from table above): | [8 empty] | 14.6 | 0.14973
[11 empty] | 15.3 | 0.31225
|  |  | Path |  | E(t) | spath | Probability |  |  |  | 16 | 0.39894
|  | 2 | 1-3-6-8 |  | 16 | 1 | 0.84134 |  |  |  | 16.7 | 0.31225
[11 empty] | 17.4 | 0.14973
[11 empty] | 18.1 | 0.043984
[11 empty] | 18.8 | 0.0079155
[11 empty] | 19.5 | 0.00087268
[11 empty] | 17 |  | 0
[11 empty] | 17 |  | 0.39894
[11 empty] | 6.2648 | 46 | 0
[11 empty] | 19.7352 | 19.7352 | 0

## Example 17
Time-Cost Tradeoffs: Crashing
| Note: | use AOA notation with ascending nodes numbers from beginning to end.
<Back |  | Step 1: | Enter Activity, Start, End, Normal Time data. Initially Crashing Time and Cost
columns must be blank. (Note: delete F14:G43 below to re-start problem.)
|  | Step 2: | Press Solve
|  | Step 3: | Select feasible activity(ies) on critical path(s) to crash, if there are no feasible
activities, you are done.
|  | Step 4: | Enter Crashing Time and Cost in the row(s) for activity(ies) selected in step 3.
Go to Step 2.
[11 empty] | Project Completion Time: | 17
[11 empty] | Crashing Cost: | 1700
|  |  |  | Normal | Crashing
| Activity | Start | End | Time | Time | Cost | Time | ES | EF | LF | LS | Slack
| a | 1 | 2 | 6 |  |  | 6 | 0 | 6 | 6 | 0 | 0 | See steps in
| b | 2 | 5 | 10 |  |  | 10 | 6 | 16 | 16 | 6 | 0 | solution below.
| c | 1 | 3 | 5 | 1 | 300 | 4 | 0 | 4 | 4 | 0 | 0
| d | 3 | 4 | 4 |  |  | 4 | 4 | 8 | 8 | 4 | 0
| e | 4 | 5 | 9 | 1 | 600 | 8 | 8 | 16 | 16 | 8 | 0
| f | 5 | 6 | 2 | 1 | 800 | 1 | 16 | 17 | 17 | 16 | 0
Copy of steps in solution:
| Initial solution: | [10 empty] | Project Completion Time: | 20
[12 empty] | Crashing Cost: | 0
[5 empty] | Normal | Crashing
|  | Activity | Start | End | Time | Time | Cost | Time | ES | EF | LF | LS | Slack
|  | a | 1 | 2 | 6 |  |  | 6 | 0 | 6 | 8 | 2 | 2
|  | b | 2 | 5 | 10 |  |  | 10 | 6 | 16 | 18 | 8 | 2
|  | c | 1 | 3 | 5 |  |  | 5 | 0 | 5 | 5 | 0 | 0
|  | d | 3 | 4 | 4 |  |  | 4 | 5 | 9 | 9 | 5 | 0
|  | e | 4 | 5 | 9 |  |  | 9 | 9 | 18 | 18 | 9 | 0
|  | f | 5 | 6 | 2 |  |  | 2 | 18 | 20 | 20 | 18 | 0
| Crash activity c by 1 day, cost 300: | [10 empty] | Project Completion Time: | 19
[12 empty] | Crashing Cost: | 300
[5 empty] | Normal | Crashing
|  | Activity | Start | End | Time | Time | Cost | Time | ES | EF | LF | LS | Slack
|  | a | 1 | 2 | 6 |  |  | 6 | 0 | 6 | 7 | 1 | 1
|  | b | 2 | 5 | 10 |  |  | 10 | 6 | 16 | 17 | 7 | 1
|  | c | 1 | 3 | 5 | 1 | 300 | 4 | 0 | 4 | 4 | 0 | 0
|  | d | 3 | 4 | 4 |  |  | 4 | 4 | 8 | 8 | 4 | 0
|  | e | 4 | 5 | 9 |  |  | 9 | 8 | 17 | 17 | 8 | 0
|  | f | 5 | 6 | 2 |  |  | 2 | 17 | 19 | 19 | 17 | 0
| Crash activity e by 1 day, cost 600: | [10 empty] | Project Completion Time: | 18
[12 empty] | Crashing Cost: | 900
[5 empty] | Normal | Crashing
|  | Activity | Start | End | Time | Time | Cost | Time | ES | EF | LF | LS | Slack
|  | a | 1 | 2 | 6 |  |  | 6 | 0 | 6 | 6 | 0 | 0
|  | b | 2 | 5 | 10 |  |  | 10 | 6 | 16 | 16 | 6 | 0
|  | c | 1 | 3 | 5 | 1 | 300 | 4 | 0 | 4 | 4 | 0 | 0
|  | d | 3 | 4 | 4 |  |  | 4 | 4 | 8 | 8 | 4 | 0
|  | e | 4 | 5 | 9 | 1 | 600 | 8 | 8 | 16 | 16 | 8 | 0
|  | f | 5 | 6 | 2 |  |  | 2 | 16 | 18 | 18 | 16 | 0
| Crash activity f by 1 day, cost 800: | [10 empty] | Project Completion Time: | 17
[12 empty] | Crashing Cost: | 1700
[5 empty] | Normal | Crashing
|  | Activity | Start | End | Time | Time | Cost | Time | ES | EF | LF | LS | Slack
|  | a | 1 | 2 | 6 |  |  | 6 | 0 | 6 | 6 | 0 | 0
|  | b | 2 | 5 | 10 |  |  | 10 | 6 | 16 | 16 | 6 | 0
|  | c | 1 | 3 | 5 | 1 | 300 | 4 | 0 | 4 | 4 | 0 | 0
|  | d | 3 | 4 | 4 |  |  | 4 | 4 | 8 | 8 | 4 | 0
|  | e | 4 | 5 | 9 | 1 | 600 | 8 | 8 | 16 | 16 | 8 | 0
|  | f | 5 | 6 | 2 | 1 | 800 | 1 | 16 | 17 | 17 | 16 | 0

## Solved Problem 1
Pert/CPM with Deterministic Time Estimates
Note: use AOA notation with ascending nodes numbers from beginning to end.
<Back
Note: delete cells F6:J35 to demonstrate solution.
| Activity | Start | End | Time | ES | EF | LF | LS | Slack
| a | 1 | 2 | 5 | 0 | 5 | 5 | 0 | 0
| b | 2 | 6 | 7 | 5 | 12 | 15 | 8 | 3
| c | 2 | 5 | 8 | 5 | 13 | 13 | 5 | 0
| d | 5 | 6 | 2 | 13 | 15 | 15 | 13 | 0
| e | 1 | 3 | 3 | 0 | 3 | 19 | 16 | 16
| f | 3 | 8 | 6 | 3 | 9 | 25 | 19 | 16
| g | 1 | 4 | 1 | 0 | 1 | 14 | 13 | 13
| h | 4 | 7 | 2 | 1 | 3 | 16 | 14 | 13
| i | 6 | 8 | 10 | 15 | 25 | 25 | 15 | 0
| k | 7 | 9 | 17 | 3 | 20 | 33 | 16 | 13
| m | 8 | 9 | 8 | 25 | 33 | 33 | 25 | 0

## Solved Problem 2
Pert/CPM with Deterministic Time Estimates
Note: use AOA notation with ascending nodes numbers from beginning to end.
<Back
Note: delete cells F6:J35 to demonstrate solution.
| Activity | Start | End | Time | ES | EF | LF | LS | Slack
| 1-2 | 1 | 2 | 4 | 0 | 4 | 11 | 7 | 7
| 2-5 | 2 | 5 | 6 | 4 | 10 | 17 | 11 | 7
| 2-4 | 2 | 4 | 2 | 4 | 6 | 14 | 12 | 8
| 1-3 | 1 | 3 | 9 | 0 | 9 | 9 | 0 | 0
| 3-4 | 3 | 4 | 5 | 9 | 14 | 14 | 9 | 0
| 4-5 | 4 | 5 | 3 | 14 | 17 | 17 | 14 | 0

## Solved Problem 3
Pert/CPM, Probabilistic Completion Time
<Back
|  | Path | Expected Times |  |  |  |  | E(t) | Variances |  |  |  |  | spath | Probability
| 1 | 1-2-5-8 | 16 | 11 | 24 |  |  | 51 | 0.69 | 0.69 | 0.11 |  |  | 1.2207 | 0.20633
| 2 | 1-2-6-8 | 5 | 18 | 26 |  |  | 49 | 0 | 0.25 | 0.11 |  |  | 0.6 | 0.95221
| 3 | 1-3-4-7-8 | 5 | 10 | 14 | 12 |  | 41 | 0 | 0.25 | 0.36 | 0.11 |  | 0.84853 | 1
4
5
6
7
8
[7 empty] | Projected Completion Time: | 50 | [5 empty] | Probability of Completion: | 0.19647
[11 empty] | 46.7277 | 0.00071493
[11 empty] | 47.5822 | 0.0064846
|  | Probability of completion for single path | [8 empty] | 48.4366 | 0.036033
|  | (select path number from table above): | [8 empty] | 49.2911 | 0.12266
[11 empty] | 50.1455 | 0.25581
|  |  | Path |  | E(t) | spath | Probability |  |  |  | 51 | 0.32683
|  | 1 | 1-2-5-8 |  | 51 | 1.2207 | 0.20633 |  |  |  | 51.8545 | 0.25581
[11 empty] | 52.7089 | 0.12266
[11 empty] | 53.5634 | 0.036033
[11 empty] | 54.4178 | 0.0064846
[11 empty] | 55.2723 | 0.00071493
[11 empty] | 50 |  | 0
[11 empty] | 50 |  | 0.32683
[11 empty] | 36.7277 | 46 | 0
[11 empty] | 55.2723 | 55.2723 | 0

## Solved Problem 4
Time-Cost Tradeoffs: Crashing
| Note: | use AOA notation with ascending nodes numbers from beginning to end.
<Back |  | Step 1: | Enter Activity, Start, End, Normal Time data. Initially Crashing Time and Cost
columns must be blank. (Note: delete F14:G43 below to re-start problem.)
|  | Step 2: | Press Solve
|  | Step 3: | Select feasible activity(ies) on critical path(s) to crash, if there are no feasible
activities, you are done.
|  | Step 4: | Enter Crashing Time and Cost in the row(s) for activity(ies) selected in step 3.
Go to Step 2.
[11 empty] | Project Completion Time: | 21
[11 empty] | Crashing Cost: | 19000
|  |  |  | Normal | Crashing
| Activity | Start | End | Time | Time | Cost | Time | ES | EF | LF | LS | Slack
| a | 1 | 2 | 10 |  |  | 10 | 0 | 10 | 10 | 0 | 0 | See steps in
| b | 2 | 5 | 14 | 3 | 11000 | 11 | 10 | 21 | 21 | 10 | 0 | solution below.
| c | 1 | 3 | 13 |  |  | 13 | 0 | 13 | 15 | 2 | 2
| d | 3 | 5 | 6 |  |  | 6 | 13 | 19 | 21 | 15 | 2
| e | 1 | 4 | 15 | 1 | 6000 | 14 | 0 | 14 | 14 | 0 | 0
| f | 4 | 5 | 8 | 1 | 2000 | 7 | 14 | 21 | 21 | 14 | 0
Copy of steps in solution:
| Initial Solution: | [10 empty] | Project Completion Time: | 24
[12 empty] | Crashing Cost: | 0
[5 empty] | Normal | Crashing
|  | Activity | Start | End | Time | Time | Cost | Time | ES | EF | LF | LS | Slack
|  | a | 1 | 2 | 10 |  |  | 10 | 0 | 10 | 10 | 0 | 0
|  | b | 2 | 5 | 14 |  |  | 14 | 10 | 24 | 24 | 10 | 0
|  | c | 1 | 3 | 13 |  |  | 13 | 0 | 13 | 18 | 5 | 5
|  | d | 3 | 5 | 6 |  |  | 6 | 13 | 19 | 24 | 18 | 5
|  | e | 1 | 4 | 15 |  |  | 15 | 0 | 15 | 16 | 1 | 1
|  | f | 4 | 5 | 8 |  |  | 8 | 15 | 23 | 24 | 16 | 1
| Crash b 1 week, cost 3000: | [10 empty] | Project Completion Time: | 23
[12 empty] | Crashing Cost: | 3000
[5 empty] | Normal | Crashing
|  | Activity | Start | End | Time | Time | Cost | Time | ES | EF | LF | LS | Slack
|  | a | 1 | 2 | 10 |  |  | 10 | 0 | 10 | 10 | 0 | 0
|  | b | 2 | 5 | 14 | 1 | 3000 | 13 | 10 | 23 | 23 | 10 | 0
|  | c | 1 | 3 | 13 |  |  | 13 | 0 | 13 | 17 | 4 | 4
|  | d | 3 | 5 | 6 |  |  | 6 | 13 | 19 | 23 | 17 | 4
|  | e | 1 | 4 | 15 |  |  | 15 | 0 | 15 | 15 | 0 | 0
|  | f | 4 | 5 | 8 |  |  | 8 | 15 | 23 | 23 | 15 | 0
| Crash b a second week, cost 4000, crash f by 1 week, cost 2000: | [10 empty] | Project Completion Time: | 22
[12 empty] | Crashing Cost: | 9000
[5 empty] | Normal | Crashing
|  | Activity | Start | End | Time | Time | Cost | Time | ES | EF | LF | LS | Slack
|  | a | 1 | 2 | 10 |  |  | 10 | 0 | 10 | 10 | 0 | 0
|  | b | 2 | 5 | 14 | 2 | 7000 | 12 | 10 | 22 | 22 | 10 | 0
|  | c | 1 | 3 | 13 |  |  | 13 | 0 | 13 | 16 | 3 | 3
|  | d | 3 | 5 | 6 |  |  | 6 | 13 | 19 | 22 | 16 | 3
|  | e | 1 | 4 | 15 |  |  | 15 | 0 | 15 | 15 | 0 | 0
|  | f | 4 | 5 | 8 | 1 | 2000 | 7 | 15 | 22 | 22 | 15 | 0
| Crash b a third week, cost 4000, crash e by 1 week, cost 6000: | [10 empty] | Project Completion Time: | 21
[12 empty] | Crashing Cost: | 19000
[5 empty] | Normal | Crashing
|  | Activity | Start | End | Time | Time | Cost | Time | ES | EF | LF | LS | Slack
|  | a | 1 | 2 | 10 |  |  | 10 | 0 | 10 | 10 | 0 | 0
|  | b | 2 | 5 | 14 | 3 | 11000 | 11 | 10 | 21 | 21 | 10 | 0
|  | c | 1 | 3 | 13 |  |  | 13 | 0 | 13 | 15 | 2 | 2
|  | d | 3 | 5 | 6 |  |  | 6 | 13 | 19 | 21 | 15 | 2
|  | e | 1 | 4 | 15 | 1 | 6000 | 14 | 0 | 14 | 14 | 0 | 0
|  | f | 4 | 5 | 8 | 1 | 2000 | 7 | 14 | 21 | 21 | 14 | 0