## PERT Cost
Reliable's Early Start Schedule of Costs
Estimated
|  | Duration | Estimated | Start | Cost Per Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Range Name | Cells
| Activity | (weeks) | Cost | Time | of Its Duration | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | Activity | B6:B19
| A | 2 | 180000 | 0 | 90000 | 90000 | 90000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CostPerWeek | F6:F19
| B | 4 | 320000 | 2 | 80000 | 0 | 0 | 80000 | 80000 | 80000 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CumulativeProjectCost | G22:AY22
| C | 10 | 620000 | 6 | 62000 | 0 | 0 | 0 | 0 | 0 | 0 | 62000 | 62000 | 62000 | 62000 | 62000 | 62000 | 62000 | 62000 | 62000 | 62000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EstimatedCost | D6:D19
| D | 6 | 260000 | 16 | 43333.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43333.3333 | 43333.3333 | 43333.3333 | 43333.3333 | 43333.3333 | 43333.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EstimatedDuration | C6:C19
| E | 4 | 410000 | 16 | 102500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 102500 | 102500 | 102500 | 102500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | StartTime | E6:E19
| F | 5 | 180000 | 20 | 36000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36000 | 36000 | 36000 | 36000 | 36000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Week | G5:AY5
| G | 7 | 900000 | 22 | 128571.4286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 128571.4286 | 128571.4286 | 128571.4286 | 128571.4286 | 128571.4286 | 128571.4286 | 128571.4286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | WeeklyProjectCost | G21:AY21
| H | 9 | 200000 | 29 | 22222.2222 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22222.2222 | 22222.2222 | 22222.2222 | 22222.2222 | 22222.2222 | 22222.2222 | 22222.2222 | 22222.2222 | 22222.2222 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| I | 7 | 210000 | 16 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 30000 | 30000 | 30000 | 30000 | 30000 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| J | 8 | 430000 | 25 | 53750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53750 | 53750 | 53750 | 53750 | 53750 | 53750 | 53750 | 53750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| K | 4 | 160000 | 33 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 | 40000 | 40000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| L | 5 | 250000 | 33 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 50000 | 50000 | 50000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| M | 2 | 100000 | 38 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 50000 | 0 | 0 | 0 | 0 | 0
| N | 6 | 330000 | 38 | 55000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55000 | 55000 | 55000 | 55000 | 55000 | 55000 | 0
[5 empty] | Weekly Project Cost | 90000 | 90000 | 80000 | 80000 | 80000 | 80000 | 62000 | 62000 | 62000 | 62000 | 62000 | 62000 | 62000 | 62000 | 62000 | 62000 | 175833.3333 | 175833.3333 | 175833.3333 | 175833.3333 | 109333.3333 | 109333.3333 | 194571.4286 | 164571.4286 | 164571.4286 | 182321.4286 | 182321.4286 | 182321.4286 | 182321.4286 | 75972.2222 | 75972.2222 | 75972.2222 | 75972.2222 | 112222.2222 | 112222.2222 | 112222.2222 | 112222.2222 | 72222.2222 | 105000 | 105000 | 55000 | 55000 | 55000 | 55000 | 0
[5 empty] | Cumulative Project Cost | 90000 | 180000 | 260000 | 340000 | 420000 | 500000 | 562000 | 624000 | 686000 | 748000 | 810000 | 872000 | 934000 | 996000 | 1058000 | 1120000 | 1295833.3333 | 1471666.6667 | 1647500 | 1823333.3333 | 1932666.6667 | 2042000 | 2236571.4286 | 2401142.8571 | 2565714.2857 | 2748035.7143 | 2930357.1429 | 3112678.5714 | 3295000 | 3370972.2222 | 3446944.4444 | 3522916.6667 | 3598888.8889 | 3711111.1111 | 3823333.3333 | 3935555.5556 | 4047777.7778 | 4120000 | 4225000 | 4330000 | 4385000 | 4440000 | 4495000 | 4550000 | 4550000