## PERT
Template for PERT Three-Estimate Approach
|  |  | Time Estimates |  | On Mean
| Activity | o | m | p | Critical Path | m | s2 |  |  | Range Name | Cells
| A | 1 | 2 | 3 | * | 2 | 0.11111 | Mean Critical |  | Activity | B5:B18
| B | 2 | 3.5 | 8 | * | 4 | 1 | Path |  | ActivityMean | G5:G18
| C | 6 | 9 | 18 | * | 10 | 4 | m = | 44 | ActivityVariance | H5:H18
| D | 4 | 5.5 | 10 |  | 6 | 1 | s2 = | 9 | CompletionProbability | K10
| E | 1 | 4.5 | 5 | * | 4 | 0.44444 |  |  | CriticalPathMean | K7
| F | 4 | 4 | 10 | * | 5 | 1 | P(T<=d) = | 0.84134 | CriticalPathVariance | K8
| G | 5 | 6.5 | 11 |  | 7 | 1 | where |  | d | K12
| H | 5 | 8 | 17 |  | 9 | 4 | d = | 47 | m | D5:D18
| I | 3 | 7.5 | 9 |  | 7 | 1 |  |  | o | C5:C18
| J | 3 | 9 | 9 | * | 8 | 1 |  |  | OnMeanCriticalPath | F5:F18
| K | 4 | 4 | 4 |  | 4 | 0 |  |  | p | E5:E18
| L | 1 | 5.5 | 7 | * | 5 | 1
| M | 1 | 2 | 3 |  | 2 | 0.11111
| N | 5 | 5.5 | 9 | * | 6 | 0.44444