## Reliable
Reliable Construction Co. Project Scheduling Problem
| Activity | Description | Time | ES | EF | LS | LF | Slack | Critical? | Range Name | Cells
| A | Excavate | 2 | 0 | 2 | 0 | 2 | 0 | Yes | Activity | B4:B17
| B | Foundation | 4 | 2 | 6 | 2 | 6 | 0 | Yes | Critical? | J4:J17
| C | Rough Wall | 10 | 6 | 16 | 6 | 16 | 0 | Yes | Description | C4:C17
| D | Roof | 6 | 16 | 22 | 20 | 26 | 4 | No | EF | F4:F17
| E | Exterior Plumbing | 4 | 16 | 20 | 16 | 20 | 0 | Yes | ES | E4:E17
| F | Interior Plumbing | 5 | 20 | 25 | 20 | 25 | 0 | Yes | LF | H4:H17
| G | Exterior Siding | 7 | 22 | 29 | 26 | 33 | 4 | No | LS | G4:G17
| H | Exterior Painting | 9 | 29 | 38 | 33 | 42 | 4 | No | ProjectDuration | F19
| I | Electrical Work | 7 | 16 | 23 | 18 | 25 | 2 | No | Slack | I4:I17
| J | Wallboard | 8 | 25 | 33 | 25 | 33 | 0 | Yes | Time | D4:D17
| K | Flooring | 4 | 33 | 37 | 34 | 38 | 1 | No
| L | Interior Painting | 5 | 33 | 38 | 33 | 38 | 0 | Yes
| M | Exterior Fixtures | 2 | 38 | 40 | 42 | 44 | 4 | No
| N | Interior Fixtures | 6 | 38 | 44 | 38 | 44 | 0 | Yes
|  |  |  | Project Duration | 44