## Reliable
Reliable Construction
|  |  | Immediate | Estimated | Start |  | From | To
| Activity | Activity Description | Predecessors | Duration (wks) | Time |  | Start | A
| A | Excavate |  | 2 | 0 |  | A | B
| B | Lay the foundation | A | 4 | 2 |  | B | C
| C | Put up the rough wall | B | 10 | 6 |  | C | D
| D | Put up the roof | C | 6 | 16 |  | C | E
| E | Install the exterior plumbing | C | 4 | 16 |  | C | I
| F | Install the interior plumbing | E | 5 | 20 |  | D | G
| G | Put up the exterior siding | D | 7 | 22 |  | E | F
| H | Do the exterior painting | E,G | 9 | 29 |  | E | H
| I | Do the electrical work | C | 7 | 18 |  | F | J
| J | Put up the wallboard | F,I | 8 | 25 |  | G | H
| K | Install the flooring | J | 4 | 33 |  | H | M
| L | Do the interior painting | J | 5 | 33 |  | I | J
| M | Install the exterior fixtures | H | 2 | 42 |  | J | K
| N | Install the interior fixtures | K,L | 6 | 38 |  | J | L
| Finish |  |  | 0 | 44 | Finish Time | K | N
[5 empty] | Optimal solution found |  | L | N
[7 empty] | M | Finish
[7 empty] | N | Finish

## MPL
TITLE
CriticalPath;
OPTIONS
ExcelWorkbook="Exmpl_10.8-1_CriticalPath.xls"
ExcelSheetName="Reliable"
INDEX
act := EXCELRANGE("Act");
act2 := act;
Path[act,act2] := EXCELRANGE("Path");
DATA
Duration[act] := EXCELRANGE("Duration");
VARIABLES
StartTime[act] -> ""
EXPORT TO EXCELRANGE("StartTime");
MODEL
MIN FinishTime
EXPORT TO EXCELRANGE("FinishTime")
= StartTime[Finish];
SUBJECT TO
SeqRelation[act,act2 IN Path]:
StartTime[act] + Duration[act]
<=
StartTime[act:=act2];
END